## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02. Service Management | 2.01 | 02.01 Manage Services | Implement API | 09/29/2023 | 10/13/2023 | 100% | Rushda Mansuri
2 | 02. Service Management | 2.01 | 02.01 Manage Services | Search for a proper API | 09/29/2023 | 10/13/2023 | 100% | Sai Teja Malladi
3 | 02. Service Management | 2.01 | 02.01 Manage Services | Implement core functionality | 09/29/2023 | 10/13/2023 | 100% | Tahera Shaikh
4 | 02. Service Management | 2.01 | 02.01 Manage Services | Implement GUI requirments | 10/01/2023 | 10/13/2023 | 100% | Jahid Hasan
5 | 02. Service Management | 2.01 | 02.01 Manage Services | Display all Services | 10/01/2023 | 10/13/2023 | 100% | Amala Natu
6 | 02. Service Management | 2.01 | 02.01 Manage Services | Develop test Cases for Service Details functionality | 10/03/2023 | 10/13/2023 | 100% | Bhakti Palkar
7 | 02. Service Management | 2.01 | 02.01 Manage Services | Display Notification to take Subscription | 10/05/2023 | 10/13/2023 | 100% | Rushda Mansuri
8 | 02. Service Management | 2.01 | 02.01 Manage Services | Display a form to Edit Service Details | 10/05/2023 | 10/13/2023 | 100% | Manish Avasarala
9 | 02. Service Management | 2.01 | 02.01 Manage Services | Create Add Button to Add service | 10/05/2023 | 10/13/2023 | 100% | Nidhi Berde
10 | 02. Service Management | 2.01 | 02.01 Manage Services | Create Delete Button to Delete Service | 10/07/2023 | 10/13/2023 | 100% | Jahid Hasan
11 | 02. Service Management | 2.01 | 02.01 Manage Services | Create an update and submit button | 10/07/2023 | 10/13/2023 | 100% | Manish Avasarala
12 | 02. Service Management | 2.01 | 02.01 Manage Services | Show the Service Rating | 10/07/2023 | 10/07/2023 | 100% | Rushda Mansuri
13 | 02. Service Management | 2.01 | 02.01 Manage Services | Design Test Cases | 10/07/2023 | 10/07/2023 | 100% | Rushda Mansuri
14 | 02. Service Management | 2.01 | 02.01 Manage Services | Execute Testing | 10/07/2023 | 10/07/2023 | 100% | Bhakti Palkar
15 | 02. Service Management | 2.02 | 02.02 Add Favourites | Create Add Button to Add service | 10/09/2023 | 10/13/2023 | 100% | Nidhi Berde
16 | 02. Service Management | 2.02 | 02.02 Add Favourites | Create Delete Button to Delete from favourite | 10/09/2023 | 10/13/2023 | 100% | Sai Teja Malladi
17 | 02. Service Management | 2.02 | 02.02 Add Favourites | Create an update and submit button | 10/09/2023 | 10/13/2023 | 100% | Amala Natu
18 | 02. Service Management | 2.02 | 02.02 Add Favourites | Show the Service Rating | 10/09/2023 | 10/13/2023 | 100% | Jahid Hasan
19 | 02. Service Management | 2.02 | 02.02 Add Favourites | Display all favourite Services | 10/09/2023 | 10/13/2023 | 100% | Bhakti Palkar
20 | 02. Service Management | 2.02 | 02.02 Add Favourites | Search for a proper API | 10/09/2023 | 10/13/2023 | 100% | Jahid Hasan
21 | 02. Service Management | 2.02 | 02.02 Add Favourites | Implement GUI requirments | 10/09/2023 | 10/13/2023 | 100% | Rushda Mansuri
22 | 02. Service Management | 2.02 | 02.02 Add Favourites | Design Test Cases | 10/09/2023 | 10/13/2023 | 90% | Jahid Hasan
23 | 02. Service Management | 3.02 | 02.02 Add Favourites | Execute Testing | 10/09/2024 | 10/13/2024 | 90% | Jahid Hasan

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 01. Account Management | 1.06 | 01.06 Track Loyalty | Implement API | 2023-10-14 | 2023-10-16 | 100% | Rushda Mansuri
2 | 01. Account Management | 1.06 | 01.06 Track Loyalty | Search for a proper API | 2023-10-14 | 2023-10-16 | 100% | Sai Teja Malladi
3 | 01. Account Management | 1.06 | 01.06 Track Loyalty | Implement core functionality | 2023-10-14 | 2023-10-16 | 100% | Tahera Shaikh
4 | 01. Account Management | 1.06 | 01.06 Track Loyalty | Implement GUI requirments for user history page | 2023-10-14 | 2023-10-16 | 100% | Jahid Hasan
5 | 01. Account Management | 1.06 | 01.06 Track Loyalty | Implement internal dashboard | 2023-10-14 | 2023-10-16 | 100% | Amala Natu
6 | 01. Account Management | 1.06 | 01.06 Track Loyalty | Develop test Cases for track loyalty functionality | 2023-10-14 | 2023-10-16 | 100% | Bhakti Palkar
7 | 02. Service Management | 2.03 | 02.03 Book a Service | cerate desciption page for a service | 2023-10-16 | 2023-10-21 | 100% | Rushda Mansuri
8 | 02. Service Management | 2.03 | 02.03 Book a Service | create page for displaying statistics and other data | 2023-10-16 | 2023-10-21 | 100% | Manish Avasarala
9 | 02. Service Management | 2.03 | 02.03 Book a Service | create booking details page | 2023-10-16 | 2023-10-21 | 100% | Rushda Mansuri
10 | 02. Service Management | 2.03 | 02.03 Book a Service | create order history page | 2023-10-16 | 2023-10-21 | 100% | Jahid Hasan
11 | 02. Service Management | 2.03 | 02.03 Book a Service | create add to cart button | 2023-10-16 | 2023-10-20 | 100% | Nidhi Berde
12 | 02. Service Management | 2.03 | 02.03 Book a Service | Create and Add Database tables - CartDetails, BookingDetails, RatingsDetails, UserHistory | 2023-10-16 | 2023-10-20 | 100% | Manish Avasarala
13 | 02. Service Management | 2.03 | 02.03 Book a Service | design and test the functionality | 2023-10-17 | 2023-10-21 | 100% | Jahid Hasan
14 | 02. Service Management | 2.04 | 02.04 Give Ratings/ Reviews | create a section to put in ratings on the services page | 2023-10-17 | 2023-10-21 | 100% | Manish Avasarala
15 | 02. Service Management | 2.04 | 02.04 Give Ratings/ Reviews | Design Test Cases | 2023-10-17 | 2023-10-21 | 100% | Rushda Mansuri
16 | 02. Service Management | 2.04 | 02.04 Give Ratings/ Reviews | Execute Testing | 2023-10-19 | 2023-10-21 | 100% | Rushda Mansuri
17 | 03. Advertising | 3.03 | 03.03 Post Statistical Data | Create section on services page to display statistics | 2023-10-21 | 2023-11-03 | 100% | Jahid Hasan
18 | 03. Advertising | 3.03 | 03.03 Post Statistical Data | Create button in service provider's profile to add data related to the service | 2023-10-21 | 2023-11-03 | 100% | Bhakti Palkar
19 | 03. Advertising | 3.03 | 03.03 Post Statistical Data | Implement GUI requirments | 2023-10-23 | 2023-11-03 | 100% | Jahid Hasan
20 | 03. Advertising | 3.03 | 03.03 Post Statistical Data | Design Test Cases | 2023-10-25 | 2023-11-03 | 100% | Jahid Hasan
21 | 03. Advertising | 3.03 | 03.03 Post Statistical Data | Execute Testing | 2023-10-26 | 2023-11-03 | 100% | Jahid Hasan