## Road Map
MaidEase
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/13/2023 | Iteration 2 - 11/03/2023 | Iteration 3- 11/17/2023 | Iteration 4 - 12/15/2023
01.Account Management | 01.01 Create Account
01.02 Authenicate Account
01.03 Update Account
01.04 Maintain Account Summary
01.05 Close Account
| 01.06 Track Loyalty | 4 |  | X
02. Service Management | 02.01 Manage Services | 5 | X
| 02.02 Add Favourites | 4 | X
| 02.03 Book a Service | 2 |  | X
| 02.04 Give Ratings/ Reviews | 2 |  | X
| 02.05 Modify Appointment | 5 |  |  | X
| 02.06 Send Remainder | 4 |  |  | X
03. Advertising | 03.01 Post Statistical Data | 3 |  | X
04. Finance Management | 04.01 Define Payment Mehtod | 4 |  |  |  | X
| 04.02 Validate Payment | 5 |  |  |  | X
|  | VELOCITY: | 9 | 11 | 9 | 9

## Story Map
Epics |  | MaidEase - User Story Map
Epic 1 - Account Management |  | Epic 1 -Account Management | Epic 2 - Service Management | Epic 3 - Advertising | Epic 4 -Finance Management
Epic 2 - Service Management | User Stories |  | 02.01 Manage Services |  |  | Iteration 1
Epic 3 - Advertising |  |  | 02.02 Add Favourites
Epic 4 - Finance Management
Epic 5 - Customer Support |  | 01.06 Track Loyalty | 02.03 Book a Service | 03.01 Post Statistical Data
|  |  | 02.04 Give Ratings/ Reviews |  |  | Iteration 2
02.05 Modify Appointment
|  |  | 02.06 Send Remainder |  |  | Iteration 3
04.01 Define Payment Mehtod
04.02 Validate Payment
Iteration 4