## R2 I3
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I3 | 02. Service Management | 2.05 | Modify Appointment | Create wireframes or mockups for the user interface (UI) of the "Modify Appointment" screen. Consider the input fields, date/time pickers, and any additional features. | 2023-04-11 | 2023-10-11 | 100% | Rushda Mansuri
2 | R2 - I3 | 02. Service Management | 2.05 | Modify Appointment | Implement form validation and handle user input appropriately. | 2023-04-11 | 2023-10-11 | 100% | Rushda Mansuri
3 | R2 - I3 | 02. Service Management | 2.05 | Modify Appointment | Connecting frontend to the backend API endpoints for creating and modifying appointments. Implement error handling and feedback to users. | 2023-04-11 | 2023-10-11 | 100% | Rushda Mansuri
4 | R2 - I3 | 02. Service Management | 2.05 | Modify Appointment | Implement a secure authentication system to ensure that only authorized users can create or modify appointments. | 2023-04-11 | 2023-10-11 | 100% | Rushda Mansuri
5 | R2 - I3 | 02. Service Management | 2.05 | Modify Appointment | Test the feature with various scenarios, including valid and invalid inputs, to ensure robust functionality. | 2023-04-11 | 2023-10-11 | 100% | Rushda Mansuri
6 | R2 - I3 | 02. Service Management | 2.05 | Modify Appointment | Collect user feedback after the feature is deployed to identify any improvements or additional features that users may desire. | 2023-04-11 | 2023-10-11 | 100% | Rushda Mansuri
7 | R2 - I3 | 02. Service Management | 2.06 | Send Remainder | Identify the type of reminders, target users, and the frequency of reminders. | 2023-11-11 | 2023-11-14 | 100% | Sai Manish Avasarala
8 | R2 - I3 | 02. Service Management | 2.06 | Send Remainder | Create wireframes or mockups for the user interface (UI) of the "Send Reminder" feature. Consider the options for setting reminders, notification preferences, and any additional configurations. | 2023-11-11 | 2023-11-14 | 100% | Sai Manish Avasarala
9 | R2 - I3 | 02. Service Management | 2.06 | Send Remainder | Create a database schema to store reminder-related data, including fields such as reminder message, target user, date/time, and any additional information. | 2023-11-11 | 2023-11-14 | 100% | Sai Manish Avasarala
10 | R2 - I3 | 02. Service Management | 2.06 | Send Remainder | Implement logic to handle the scheduling of reminder notifications. | 2023-11-11 | 2023-11-14 | 100% | Sai Manish Avasarala
11 | R2 - I3 | 02. Service Management | 2.06 | Send Remainder | Develop the frontend components for setting up reminders. Implement user interfaces for viewing and managing existing reminders. | 2023-11-11 | 2023-11-14 | 100% | Sai Manish Avasarala
12 |  | 02. Service Management | 2.06 | Send Remainder | Test the feature with various scenarios, including valid and invalid inputs, to ensure robust functionality. | 2023-11-11 | 2023-11-14 | 100% | Sai Manish Avasarala
13 | R2 - I3 | 02. Service Management | 2.06 | Send Remainder | Integrate a notification service to send actual reminders to users' devices. | 2023-11-11 | 2023-11-14 | 100% | Sai Manish Avasarala
14 | R2 - I3 | 02. Service Management | 2.06 | Send Remainder | Collect user feedback after the feature is deployed to identify any improvements or additional features that users may desire. | 2023-11-11 | 2023-11-14 | 100% | Sai Manish Avasarala

## R2 I4
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I4 | 04. Finance Management | 4.01 | Define Payment Method | Create wireframes or mockups for the user interface (UI) of the "Define Payment Method" screen. Consider the input fields, date/time pickers, select payment types, and any additional features. | 2023-04-24 | 2023-12-01 | 100% | Rushda Mansuri
2 | R2 - I4 | 04. Finance Management | 4.01 | Define Payment Method | Implement form validation and handle user input appropriately. | 2023-04-24 | 2023-12-02 | 100% | Rushda Mansuri
3 | R2 - I4 | 04. Finance Management | 4.01 | Define Payment Method | Connecting frontend to the backend API endpoints for retriving the billing data and proceed with the payment. Implement error handling and feedback to users. | 2023-04-24 | 2023-12-03 | 100% | Rushda Mansuri
4 | R2 - I4 | 04. Finance Management | 4.01 | Define Payment Method | Implement a secure authentication system to ensure that only authorized users get apporiate billing details and amount. | 2023-04-24 | 2023-12-02 | 100% | Rushda Mansuri
5 | R2 - I4 | 04. Finance Management | 4.01 | Define Payment Method | Test the feature with various scenarios, including valid and invalid inputs, to ensure robust functionality. | 2023-04-24 | 2023-12-02 | 100% | Rushda Mansuri
6 | R2 - I4 | 04. Finance Management | 4.01 | Define Payment Method | Collect user feedback after the feature is deployed to identify any improvements or additional features that users may desire. | 2023-04-24 | 2023-12-02 | 100% | Rushda Mansuri
100%
7 | R2 - I4 | 04. Finance Management | 4.02 | Validate Payment | Identify the payment method like Stripe, Paypal, or Apple Pay. | 2023-12-03 | 2023-12-11 | 100% | Sai Manish Avasarala
8 | R2 - I4 | 04. Finance Management | 4.02 | Validate Payment | Create wireframes or mockups for the user interface (UI) of the "Validate Payment" feature. Consider the input fields, date/time pickers, select payment types, and any additional features. | 2023-12-03 | 2023-12-11 | 100% | Sai Manish Avasarala
9 | R2 - I4 | 04. Finance Management | 4.02 | Validate Payment | Connecting frontend to the backend API endpoints for verifying the payment details. Implement error handling and feedback to users. | 2023-12-03 | 2023-12-12 | 100% | Nidhi Berde
10 | R2 - I4 | 04. Finance Management | 4.02 | Validate Payment | Implement logic to validate and store the payment details in database. | 2023-12-03 | 2023-12-12 | 100% | Nidhi Berde
11 | R2 - I4 | 04. Finance Management | 4.02 | Validate Payment | Test the feature with various scenarios, including valid and invalid inputs, to ensure robust functionality. | 2023-12-03 | 2023-12-13 | 100% | Nidhi Berde
12 | R2 - I4 | 04. Finance Management | 4.02 | Validate Payment | Collect user feedback after the feature is deployed to identify any improvements or additional features that users may desire. | 2023-12-03 | 2023-12-13 | 100% | Nidhi Berde
13 | R2 - I4 |  |  | Use Case Specifications | According to I4 user stories make an outline of how will system and users interact with each other. | 2023-11-24 | 2023-11-30 | 100% | Tahera Shaikh
14 | R2 - I4 |  |  | Supplementary Requirements | Create a document that summaries all the requirments for I4 user stories. | 2023-11-24 | 2023-12-02 | 100% | Rushda Mansuri
15 | R2 - I4 |  |  | UML Diagrams (Class, Sequence) | Create class and sequence diagrams that helps system and software developers to understand working for I4 user stories. | 2023-11-24 | 2023-12-04 | 100% | Jahid Hassan
16 | R2 - I4 |  |  | ER Diagrams (Conceptual, Logical) | Create a structural diagram that shows database design for I4 user stories. | 2023-11-24 | 2023-12-04 | 100% | Sai Teja Malladi
17 | R2 - I4 |  |  | Jenkins Progress Report | Create a report that shows the planned task and completed task for I4. | 2023-11-24 | 2023-12-12 | 100% | Sai Teja Malladi
18 | R2 - I4 |  |  | Use Case Diagrams | Create a behavioral diagram that outline the functionality of a system using actors and use cases for I4 user stories. | 2023-11-24 | 2023-11-30 | 100% | Amala Natu
19 | R2 - I4 |  |  | Updated RCT (planning I4 iterations) | Highlight the I4 user stories and its crosscuts that needs to be implement in I4. | 2023-11-24 | 2023-11-30 | 100% | Bhakti Palkar
20 | R2 - I4 |  |  | Actors (Entitlements specifcation tab in RCT) | Define the Actors in Entitlements tab in RCT of I4 user stories. | 2023-11-24 | 2023-12-04 | 100% | Bhakti Palkar
21 | R2 - I4 |  |  | JIRA: Update Kanban Board | Update JIRA Kanban board based on I4 user stories. | 2023-11-24 | 2023-12-12 | 100% | Tahera Shaikh
22 | R2 - I4 |  |  | qTest: Test Execution Log | Demonstrate the Test Execution logs for I4 user stories. | 2023-11-24 | 2023-12-12 | 100% | Jahid Hassan
23 | R2 - I4 |  |  | Jenkins: Complete Planned Task | Complete all the planned task mentioned in Jenkins Progress Report for I4 user stories. | 2023-11-24 | 2023-12-12 | 100% | Sai Teja Malladi