## Road Map
MaidEase
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/13/2023 | Iteration 2 - 11/03/2023 | Iteration 3- 11/17/2023 | Iteration 4 - 12/15/2023
01.Account Management | 01.01 Create Account
01.02 Authenicate Account
01.03 Update Account
01.04 Maintain Account Summary
01.05 Close Account
| 01.06 Track Loyalty | 4 |  | X
02. Service Management | 02.01 Manage Services | 5 | X
| 02.02 Add Favourites | 4 | X
| 02.03 Book a Service | 2 |  | X
| 02.04 Give Ratings/ Reviews | 2 |  | X
| 02.05 Modify Appointment | 2 |  |  | X
| 02.06 Send Remainder | 2 |  |  | X
03. Advertising | 03.01 Advertise Available Service | 3 |  |  |  | X
| 03.02 Post Discounts / Special Offers | 3 |  |  | X
| 03.03 Post Statistical Data | 4 |  | X
04. Finance Management | 04.01 Define Payment Mehtod | 3 |  |  | X
| 04.02 Validate Payment | 4 |  |  | X
| 04.03 Renew Subscription | 3 |  |  |  | X
05. Customer Support | 05.01 Generate Ticket | 2 |  |  |  | X
| 5.02 Provide Support | 2 |  |  |  | X
| 05.03 Close Ticket | 2 |  |  |  | X
|  | VELOCITY: | 9 | 11 | 14 | 12

## Story Map
Epics |  | MaidEase - User Story Map
Epic 1 - Account Management |  | Epic 1 -Account Management | Epic 2 - Service Management | Epic 3 - Advertising | Epic 4 -Finance Management | Epic 5 - Customer Support
Epic 2 - Service Management | User Stories |  | 02.01 Manage Services |  |  |  | Iteration 1
Epic 3 - Advertising |  |  | 02.02 Add Favourites
Epic 4 - Finance Management
Epic 5 - Customer Support |  | 01.06 Track Loyalty | 02.03 Book a Service | 03.03 Post Statistical Data
|  |  | 02.04 Give Ratings/ Reviews |  |  |  | Iteration 2
|  |  | 02.05 Modify Appointment | 03.02 Post Discounts / Special Offers | 04.01 Define Payment Mehtod
|  |  | 02.06 Send Remainder |  | 04.02 Validate Payment |  | Iteration 3
[5 empty] | 04.03 Renew Subscription | 05.01 Generate Ticket
|  |  |  | 03.01 Advertise Available Service |  | 5.02 Provide Support
[6 empty] | 05.03 Close Ticket | Iteration 4